# SCOPE OF WORK

## Purpose

Covered California requires the services of a Contractor, who specializes in executive recruitment, to assist in recruiting and hiring for exempt executive leadership positions on an as needed basis. Government Code section 100503(m) authorizes Covered California to “employ necessary staff” and “hire…key executive positions…who shall be exempt from civil service.” Executive leaders are responsible for advancing Covered California’s mission to increase the number of insured Californians, improve health care quality, lower costs and reduce health disparities through an innovative, competitive marketplace that empowers consumers to choose the health plan and providers that give them the best value.

These executive positions may include chief deputy executive directors, division directors, deputy directors, chief officers, and other senior leadership roles overseeing core functions such as marketing, communications, external affairs, outreach and sales, plan management, service center operations, information technology, finance, human resources, legal affairs, program integrity, policy, evaluation and research, and administration. Titles may include the positions listed below, as well as other leadership roles of comparable scope and complexity:

Chief Data and Insights Officer
Chief Deputy Executive Director, Operations
Chief Deputy Executive Director, Program (Plans, Sales & Service)
Chief Information Officer
Chief Medical Officer
Director, Communications and Public Relations
Director, Equity & Quality Transformation
Director, External Affairs and Community Engagement
Director, Financial Management Division
Director, Marketing
Director, Outreach and Sales
Director, Plan Management
Director, Policy Eligibility and Research
Executive Director
General Counsel

The Contractor shall assist Covered California to identify, recruit, and help hire the most qualified candidates to advance this mission and the strategic and operational work of Covered California’s executive leadership team.

## Background Clearance

If the Contractor must access any confidential information, this provision must be completed prior to implementing any portion of this scope of work.

Prior to accessing any confidential information, personal identifying information, personal health information, federal tax information, or financial information contained in the information systems and devices of Covered California, or any other information as required by federal and State law or guidance, all staff, including employees, contract or subcontract personnel, vendors or volunteers who perform services under this Agreement must comply with the criminal background check requirements set forth in Government Code section 1043, and its implementing regulations set forth in California Code of Regulations, Title 10, section 6456. Contractor shall bear all costs associated with obtaining clearance for each said employee.

## Amendment

Covered California may, at its sole discretion, extend the term of the Agreement for one (1) year. The total number of contract years shall not exceed four (4) years. Additional funding for any time extension will be at the same rates provided in Contractor’s proposal. All amendments for time or funds cannot exceed the limitations set forth in the solicitation that resulted in this Agreement. Amendments must also comply with Covered California’s rules and procedures governing contracts and procurements.

The parties may increase or decrease funding through an amendment, but cannot exceed the amount set by Contractor’s proposal. Funding for option years may not be used in advance and may not exceed the funding amount set in the base Agreement unless authorized by the solicitation.

This Agreement may be amended by mutual consent of the parties. No alteration or variation of the terms of this Agreement shall be valid unless made in writing and signed by the parties. No oral understanding or agreement not incorporated in the Agreement is binding on any of the parties.

## General Scope or Tasks

The Contractor will perform all services as outlined below, on an as-needed basis for one (1) or more executive recruitments during the term of the Agreement.

- Background Review and Familiarization

Prior to commencing any recruitment, the Contractor shall review key documents about the role of Covered California under the Affordable Care Act (ACA) and its implementing framework. Contractor’s review shall include, at a minimum:

- The ACA and related federal regulations applicable to state based marketplaces;

- California’s implementing statutes and regulations governing the Covered California; and

- Covered California’s strategic plans, job descriptions, organizational charts, workforce and succession planning documents, and other materials identified by Covered California.

- Discovery Meetings and Recruitment Planning

For each recruitment, the Contractor shall conduct in depth meetings with personnel identified by Covered California (e.g., the Executive Director, division leadership, Human Resources, and other stakeholders) to:

- Jointly develop timelines, goals, priorities, and expectations for the recruitment process;

- Clarify the position’s strategic role, reporting relationships, and key performance expectations; and

- Assist Covered California in developing pertinent and effective interview questions, exercises, and evaluation techniques to be used by Covered California in interviews of top candidates.

- Position-Specific Recruitment Strategy and Materials

Based on the initial research and discovery meetings, the Contractor shall, for each executive recruitment:

- Develop a recruitment strategy, position profile, and marketing materials tailored to the specific executive role; and

- Submit these materials to Covered California for review and approval prior to implementation.

- Candidate Sourcing and Marketing

Contractor shall implement the approved recruitment strategy, which may include:

- Nationwide advertising and targeted outreach for the executive position;

- Direct engagement with networks and sources experienced in health care, health insurance, government, or related fields, as appropriate to the position; and

- Coordination with Covered California, which may recommend potential candidates. If requested by Covered California, Contractor shall perform some or all of the tasks in this Scope of Work for Covered California-identified potential candidates.

- Screening and Presentation of Candidates

Contractor shall:

- Screen candidate résumés based on Covered California’s goals, expectations, and minimum and desired qualifications;

- Interview the most viable candidates, in person or remotely, to develop a final list of top candidates for Covered California’s consideration; and

- Prepare and submit for Covered California’s review and acceptance a Candidate Profile Fact Sheet (or comparable document) for each recommended candidate summarizing qualifications, experience, and other relevant information.

- Reference Checks

For the final list of top candidates for each recruitment, Contractor shall complete reference checks as directed by Covered California. Unless otherwise expressly authorized in writing by Covered California, these reference checks shall not include any background checks (e.g., criminal history, credit checks).

- Interview Coordination

Contractor shall assist Covered California in scheduling and coordinating interviews, including follow up interviews if necessary, for top candidates and finalists, consistent with Covered California’s timelines and processes.

- Offer and Negotiation Support

Contractor shall, at Covered California’s request:

- Assist in the negotiation of an employment offer to the selected candidate, including terms related to start date, compensation, and other conditions, within parameters established by Covered California; and

- Provide advice on candidate communication during the offer and acceptance period.

- Timelines and Work Plans

Executive searches of this nature typically take between five and six months to complete, from the initial discovery phase meetings to offer acceptance. At the outset of each engagement for a specific position, and within five (5) business days, Contractor shall:

- Develop a timeline and work plan tailored to that recruitment, based on Covered California’s needs and preferences; and

- Identify key milestones and decision points, including dates for candidate outreach, screening, interviews, and anticipated offer.

- Phased Work Structure

For each executive recruitment, Contractor shall perform services according to the following phases, unless otherwise agreed in writing by Covered California:

- Phase 1: Discovery and Planning

Key Activities and Deliverables

- Conduct an organizational needs analysis for the specific executive role and offer general consultation on role definition and structure.

- Develop a project communication plan and search timeline for the position.

- Identify critical leadership competencies aligned with Covered California’s mission, strategic priorities, and diversity, equity, and inclusion goals.

- Develop a full leadership profile for the position. Covered California’s search committee (as identified by Covered California) shall maintain editorial authority over the final profile.

- Establish, if requested, a secure web portal or equivalent secure platform as a repository for search and candidate materials accessible to designated Covered California personnel.

- Propose a recruitment strategy based on Covered California’s objectives and any relevant market conditions.

- Phase 2: Candidate Sourcing and Evaluation

Key Activities and Deliverables

- Maintain regular, timely communication with personnel identified by Covered California throughout the sourcing and evaluation process.

- Acknowledge nominations and applications and ensure professional, timely communication with prospects and candidates.

- Conduct proactive outreach to valuable sources and desirable prospects, including passive candidates, consistent with the approved strategy.

- Review applications and prospect credentials to assess alignment with the leadership profile and selection criteria.

- Conduct comprehensive leadership history evaluations prior to candidate presentation, including assessment of prior roles, scope of responsibility, and performance indicators where available.

- Screen for prior publicly known allegations of harassment or discrimination using reasonable, good faith methods, and report any such information to Covered California consistent with applicable law and Covered California direction.

- Deliver highly qualified candidates and corresponding materials to Covered California, including résumés, candidate profiles, and any other agreed upon documentation.

- Phase 3: Candidate Interview Support

Key Activities and Deliverables

- Assist Covered California in identifying candidates for first and second round interviews, based on agreed upon criteria.

- Coordinate logistics for first and second round candidate interviews, including scheduling, confirming participation, and providing necessary information to candidates.

- Draft tailored interview questions and share evaluation tools and methods (e.g., rating matrices, competency-based questions) for use by Covered California’s interview panels.

- Conduct additional references and, as directed by Covered California, investigate public media sources relevant to candidate reputation and professional history.

- If requested by Covered California, coordinate and/or administer leadership, executive, or other assessments (e.g., psychologist led assessments) for finalists, in accordance with applicable laws and Covered California policies.

- Phase 4: Selection and Appointment

Key Activities and Deliverables

- Advise Covered California on terms, salary, benefits, relocation (if applicable), and other offer components, consistent with Covered California’s compensation framework and applicable law.

- Debrief candidate participants once the new hire is announced, as directed by Covered California, to support positive candidate experience and maintain relationships for future recruitments.

- Provide transition and onboarding planning/support, as requested by Covered California, including suggestions for early engagement, stakeholder introductions, and initial performance focus areas to promote a successful executive transition.

## Reporting Headquarters Location

The Contractor is required to perform all services under this Agreement on site at Covered California, unless directed otherwise by the project representative listed in this Exhibit. The Covered California office is located at 1601 Exposition Boulevard, Sacramento, California, 95815. Travel and expenses for reporting to this headquarters location shall not be reimbursed.

## Reassignment of Personnel

- The Contractor shall not reassign nor substitute personnel assigned to the contract during the contract term without prior written approval of Covered California. If a Contractor employee is unable to perform duties due to illness, resignation, or other factors beyond the Contractor’s control, the Contractor shall make every reasonable effort to provide suitable substitute personnel.

- Substitute personnel shall not automatically receive the hourly rate of the individual or position being replaced. Covered California and the Contractor shall negotiate the hourly rate of any substitute personnel to the contract. The hourly rate negotiated shall be dependent, in part, on the experience and individual skills of the proposed substitute personnel. The negotiated rate cannot exceed the hourly rate stated in the contract.

- Covered California reserves the right to request a Contractor employee be removed from performing any work on the contract and, on written notice to the Contactor, the Contractor shall assign a substitute employee.

## Contractor’s Roles and Responsibilities

The Contractor shall:

- Designate a person to whom all project communications may be addressed and who has the authority to act on all aspects of the contract. This person will be responsible for the overall project and will be the contact for all invoicing and Contractor staffing issues.

- Provide written reports for review and approval by Covered California and formally respond to Covered California review findings as necessary.

- Meet as required with Covered California staff to discuss progress.

- Make its best efforts to maintain staff continuity throughout the life of the project. If, however, a substitution becomes necessary, the Contractor must submit resumes for review, in advance, for all proposed personnel substitutions. All Contractor personnel substitutions must be approved in writing by Covered California Representative. Failure to receive the required approvals may result in termination of the contract.

## Covered California’s Roles and Responsibilities

Covered California shall:

- Designate the Covered California Representative to whom all Contractor communications may be addressed and who has the authority to act on all aspects of the contract.

- Provide access to business and technical documents as necessary for the Contractor to complete the tasks identified in this Agreement.

- Ensure appropriate resources are available to perform assigned tasks, attend meetings, and answer questions.

- Ensure that decisions are made in a timely manner.

- Provide work areas and meeting rooms as needed.

- Identify and provide access to Subject Matter Experts to assist in the development of technical requirements.

## Contract Deliverables

- The Contractor understands that all recommendations and contract deliverables must comply with the Patient Protection and Affordable Care Act of 2010, as well as sections 15438, 15439, and 100501 through 100521 of the Government Code; 1346.2 and 1366.6 of the Health and Safety Code; 10112.3 and 10112.4 of the Insurance Code.

- The Contractor shall provide all deliverables within the timeframe specified and required by Covered California.

- The Contractor understands and acknowledges that all deliverables must be reviewed, approved and accepted by Covered California.

- The Contractor understands that any Covered California requested revisions to any deliverable shall be incorporated by the Contractor within seven (7) calendar days from the date in which Covered California provided its feedback, unless a different timeframe is required and specified by Covered California.

- In the event Covered California requires additional refinements and modifications for any deliverable which occurs after that deliverable has been previously accepted by Covered California, the Contractor shall be required to make the additional revisions until the revised deliverable is accepted and approved by Covered California.

- The Contractor shall be paid for services rendered under this Agreement in accordance with Exhibit B – Budget Detail and Payment Provisions.

## Deliverable Acceptance Criteria

- All concluded work must be submitted to Covered California for review and approval or rejection. It will be Covered California’s sole determination as to whether any tasks have been successfully completed and are acceptable.

- Throughout the term of the contract, Covered California will review and validate services performed. In addition, the Covered California Representative will verify and approve the Contractor’s invoices. Signed acceptance is required from the Covered California Representative to approve each invoice for payment.

- Contractor’s recommendations and contract deliverables must comply with the Patient Protection and Affordable Care Act of 2010, as well as sections 15438, 15439, and 100501 through 100521 of the Government Code; 1346.2 and 1366.6 of the Health and Safety Code; 10112.3 and 10112.4 of the Insurance Code.

- Deliverable acceptance criteria shall include, but not be limited to, the following:

- Deliverable-specific work was completed as specified and the final deliverable product or service was rendered to the satisfaction of Covered California;

- Plans, schedules, designs, documentation, digital files, photographs and reports (deliverables) were completed as specified and approved;

- All goods/equipment delivered conform to specifications and quantities, including requirements for special handling and packaging; and operability and functionality;

- All deliverable documentation and artifact gathering have been completed and delivered; and

- All deliverables are in a format useful to Covered California.

- Covered California reserves the right to review and inspect all deliverables following Contractor’s delivery of each deliverable to Covered California, and to determine whether the deliverables are satisfactory and conform to Covered California’s specifications. Covered California may, in its sole discretion, either:  a) reject a deliverable if it fails to conform to the specifications and meet Covered California’s satisfaction or has defects (collectively, “errors”); or b) may accept each deliverable if it has no such errors (“acceptance”). Covered California shall have not less than ten (10) business days from the receipt of the deliverable to either accept or reject the deliverable, unless the parties mutually agree to an alternative deadline.

- If Covered California rejects a deliverable, Covered California will notify the Contractor in writing via email or otherwise to Contractor’s representative with the reason for the rejection and a list of deficiencies. The Contractor shall promptly correct the stated deficiencies and resubmit the corrected deliverable within five (5) business days of receipt of the written notice and list of deficiencies, unless an extension is requested in writing by the Contractor and approved by Covered California. Contractor shall respond to all of Covered California’s comments, and as appropriate and necessary, incorporate such responses into its resubmission of the deliverable.

- After receipt of a corrected deliverable, Covered California shall again have the opportunity to review the resubmitted deliverable and will provide Contractor with an acceptance of that deliverable or give a notice of continuing deficiency within ten (10) business days. If notice of a continuing deficiency is given, Covered California will provide the Contractor a description of the deficiencies that continue. If Contractor fails to meet all criteria within the specified timeframes, Covered California reserves the right to; a) modify timeframes as necessary (in Covered California’s sole discretion) until Covered California is satisfied that all deliverables comply with Covered California’s specifications as required by the Agreement; or b) terminate this Agreement for cause.

- In the event Covered California fails to review and accept or reject a deliverable within ten (10) business days of receipt or such additional time as the parties may agree, the Contractor shall notify Covered California of the late response and proceed with performance as if acceptance had been received from Covered California. However, such failure by Covered California to respond shall not constitute a formal acceptance of the deliverable by Covered California. If, in such circumstances, Covered California subsequently requires material changes to the deliverable, the parties shall fairly consider and mutually agree as to the effect of the untimely rejection or acceptance on the delivery or implementation schedules. In no event shall the Contractor be entitled to any price increase due to the need to correct deficient deliverables as identified by Covered California.

Such reviews and resubmissions shall not be construed as a waiver of any   deliverable or obligation to be performed under this Agreement, nor of any scheduled deliverable due date, nor any rights or remedies provided by law or through this Agreement. Additionally, Covered California’s waiver of, or lack of objection to, a deficiency with respect to a particular deliverable or obligation shall not be construed to be a waiver of the same or a similar deficiency or obligation with respect to any other deliverable.

- As used in this section, the term “continuing deficiency” shall be limited to:

- Inadequate resolution, in the reasonable judgment of Covered California, of the items raised during the previous Covered California review;

- Related issues which were tied to or created by the method of resolving the previous Covered California comments;

- Items which could not be thoroughly tested or reviewed by Covered California because of an inadequate, incorrect or incomplete deliverable, previously submitted, which was identified as inadequate, incorrect or incomplete by Covered California’s previous written comments; and

- Omissions of parts of a deliverable.

- Unless otherwise agreed upon by Covered California, Contractor shall not delay the resubmission of a previously rejected deliverable to include the introduction of new items identified by the Contractor during subsequent reviews. Any such new items, including those items which could have been identified by a thorough review of a previously submitted deliverable, shall be considered separately under the following review process. In such circumstances, Contractor shall introduce new items to Covered California for review, and if the parties mutually agree upon the material revision of a deliverable, the parties shall fairly consider and mutually agree as to the effect of the new items on the deliverable(s) or implementation schedules.

- If deliverables are not submitted to the satisfaction of Covered California and Covered California terminates the contract, the Contractor may be held liable for any additional costs, including, but not limited to, the costs of administration and rebidding of the work to be completed. Unless otherwise agreed upon by Covered California, in no event shall the Contractor be entitled to any price increase due to any rejections, delays, resubmissions, or agreed-upon modifications of deliverables pursuant to this Section.

## Project Representatives

The representatives for this project, during the term of this Agreement, shall be:

| Covered California Representative: | Contractor Representative: |
| --- | --- |
| (Covered California Employee) Covered California 1601 Exposition Blvd. Sacramento, CA 95815 (916) XXX-XXXX T (Covered California Employee Email Address) | (Representative’s Name) (Contractor’s Name) (Address) (City, State and Zip) (916) XXX-XXXX T (Email Address) |